## Sheet1
ID | User Story | Priority | Story Points |  |  |  | Must | Should | Could | S1 | S2 | S3 | S4 | T | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Velocity
1 | Student Create account | Must Have | 6 | 1 |  |  | 6 |  |  | 1 |  |  |  | 1 | 6 | 0 | 0 | 0 | 27
2 | Student Register Class | Must Have | 9 | 1 |  |  | 9 |  |  |  | 1 |  |  | 1 | 0 | 9 | 0 | 0
3 | Student Create Profile | Should Have | 4 |  | 1 |  |  | 4 |  |  |  | 1 |  | 1 | 0 | 0 | 4 | 0
4 | Student Contact Teacher | Should Have | 2 |  | 1 |  |  | 2 |  |  |  |  | 1 | 1 | 0 | 0 | 0 | 2
5 | Admin Create Teacher Accts | Must Have | 6 | 1 |  |  | 6 |  |  | 1 |  |  |  | 1 | 6 | 0 | 0 | 0
6 | Teacher create contracts w/ Students | Must Have | 8 | 1 |  |  | 8 |  |  |  | 1 |  |  | 1 | 0 | 8 | 0 | 0
7 | Teacher view booked classes | Should Have | 3 |  | 1 |  |  | 3 |  |  | 1 |  |  | 1 | 0 | 3 | 0 | 0
8 | Homepage | Must Have | 9 | 1 |  |  | 9 |  |  | 1 |  |  |  | 1 | 9 | 0 | 0 | 0
9 | About Page | Should Have | 2 |  | 1 |  |  | 2 |  |  | 1 |  |  | 1 | 0 | 2 | 0 | 0
10 | Login Page | Must Have | 3 | 1 |  |  | 3 |  |  | 1 |  |  |  | 1 | 3 | 0 | 0 | 0
11 | Forgot Password | Should Have | 2 |  | 1 |  |  | 2 |  |  |  | 1 |  | 1 | 0 | 0 | 2 | 0
12 | Contact Page | Must Have | 2 | 1 |  |  | 2 |  |  |  | 1 |  |  | 1 | 0 | 2 | 0 | 0
13 | View Courses | Must Have | 2 | 1 |  |  | 2 |  |  |  | 1 |  |  | 1 | 0 | 2 | 0 | 0
14 | Track Instruments | Could Have | 4 |  |  | 1 |  |  | 4 |  |  | 1 |  | 1 | 0 | 0 | 4 | 0
15 | Admin Manage Teacher Contracts | Could Have | 6 |  |  | 1 |  |  | 6 |  |  |  | 1 | 1 | 0 | 0 | 0 | 6
16 | Admin get Feedback f/Studens abt Teachers | Could Have | 3 |  |  | 1 |  |  | 3 |  |  |  | 1 | 1 | 0 | 0 | 0 | 3
17 | Admin Limit Lessons for Students | Should Have | 2 |  | 1 |  |  | 2 |  |  | 1 |  |  | 1 | 0 | 2 | 0 | 0
18 | Admin Report Page | Should Have | 7 |  | 1 |  |  | 7 |  |  |  | 1 |  | 1 | 0 | 0 | 7 | 0
19 | Student hires previous instrument | Should Have | 4 |  | 1 |  |  | 4 |  |  |  | 1 |  | 1 | 0 | 0 | 4 | 0
20 | Log of previous lessons | Could Have | 3 |  |  | 1 |  |  | 3 |  |  |  | 1 | 1 | 0 | 0 | 0 | 3
21 | Logout page | Must Have | 2 | 1 |  |  | 2 |  |  | 1 |  |  |  | 1 | 2 | 0 | 0 | 0
22 | Admin Create Admin Accts | Should Have | 6 |  | 1 |  |  | 6 |  |  |  | 1 |  | 1 | 0 | 0 | 6 | 0
TOTAL |  |  | 95 | 9 | 9 | 4 | 47 | 32 | 16 | 5 | 7 | 6 | 4 |  | 26 | 28 | 27 | 14
[10 empty] | Remaining Velocity |  |  |  |  | 1 | -1 | 0 | 13
[10 empty] | Release 1 |  |  |  |  | 54
[10 empty] | Release 2 |  |  |  |  | 41